## Project Plan and Gantt
Project Name | Workflow JS Widget |  | Project Status: |  |  |  | <- | Values automatically update | Resources
Project Manager | Justin Goulet |  | Complete |  |  | 18 |  |  | Justin Goulet | Project Manager
Project Deliverable |  |  | In Progress |  |  | 3 |  |  | Chris Larsen | DBA / Developer
Scope Statement: |  |  | Not Started |  |  | 23 |  |  | Mikal Callahan | UX / UI Designer
|  |  | OverDue |  |  | 0 |  |  | Brock Corbett | Developer
Start Date | 2017-01-31 | [7 empty] | Shaun-Inn Wu | Project Director
Expected End Date | 2017-05-18 | [7 empty] | Developers | Development Team
Overall Progress | 31.58% |  | Note - Percentage is provided by ALL items completed divided by the amount of cells not empty | [5 empty] | All | Project Team
Tasks | Responsible | Start | End | Days | Hours | Status | isComplete
Introduction to Course | Project Director | 2017-01-24 | 2017-01-24 | 1 |  | Complete | 1
Syllabus / Project Introduction | Project Director | 2017-01-25 | 2017-01-31 | 6 |  | Complete | 1
Client Presentation / Team Formation | Project Director | 2017-01-31 | 2017-01-31 | 1 |  | Complete | 1
JAD 1
Meeting Agenda | Project Manager | 2017-02-07 | 2017-02-07 | 1 |  | Complete | 1
Meeting | Project Manager | 2017-02-08 | 2017-02-08 | 1 |  | Complete | 1
Meeting Notes | Project Manager | 2017-02-09 | 2017-02-09 | 1 |  | Complete | 1
Setup Client Communications | Project Manager | 2017-02-08 | 2017-02-08 | 1 |  | Complete | 1
Research Possible Workflow Solutions | Project Manager | 2017-02-09 | 2017-02-22 | 13 |  | Complete | 1
Create Sketch of Proposed Solution | Project Manager | 2017-02-22 | 2017-02-23 | 1 | 22 | Complete | 1
Report 1
Create Report | Project Team | 2017-02-10 | 2017-02-14 | 4 | 10 | Complete | 1
Feedback on Report | Project Team | 2017-02-16 | 2017-02-16 | 1 | 1 | Complete | 1
Submit Report 1 | Project Team | 2017-02-16 | 2017-02-16 | 1 | 0.25 | Complete | 1
JAD 2
Meeting Agenda | Project Manager | 2017-02-21 | 2017-02-21 | 1 | 1 | Complete | 1
Meeting | Project Team | 2017-02-22 | 2017-02-22 | 1 | 1 | Complete | 1
Meeting Notes | Project Team | 2017-02-22 | 2017-02-22 | 1 | 1 | Complete | 1
Report 2
Create Report | Project Team | 2017-02-23 | 2017-02-27 | 4 | 10 | Complete | 1
Feedback on Report | Project Team | 2017-02-28 | 2017-03-07 | 7 | 1 | In Progress
Submit Report 2 | Project Team | 2017-03-07 | 2017-03-07 | 1 | 0.25 | Not Started
Decision Matrix
D3 / D4 & Others: Cost / Features | Project Team | 2017-02-28 | 2017-03-01 | 1 |  | Complete | 1
Create Editable Decision Matrix | Project Manager | 2017-02-28 | 2017-02-28 | 1 |  | Complete | 1
Product
User Manual | Project Manager | 2017-02-28 | 2017-03-15 | 15 |  | In Progress
Skelaton Product | Development Team | 2017-02-28 | 2017-03-15 | 15 |  | In Progress
Prototype 1
Meeting Agenda | Project Manager | 2017-03-14 | 2017-03-14 | 1 | 1 | Not Started | 1
Meeting | Project Team | 2017-03-15 | 2017-03-15 | 1 | 1 | Not Started | 1
Meeting Notes | Project Team | 2017-03-15 | 2017-03-15 | 1 | 1 | Not Started | 1
Report 3
Create Report | Project Team | 2017-03-23 | 2017-03-28 | 5 | 10 | Not Started
Feedback on Report | Project Team | 2017-03-30 | 2017-03-30 | 1 | 1 | Not Started
Submit Report 3 | Project Team | 2017-04-04 | 2017-04-04 | 1 | 0.25 | Not Started
Project
Updates to current Docs | Project Manager | 2017-03-15 | 2017-03-28 | 13 |  | Not Started
Working prototype of simple theme | Development Team | 2017-03-15 | 2017-03-28 | 13 |  | Not Started
Complete code for implementing prototype | Development Team | 2017-03-15 | 2017-03-28 | 13 |  | Not Started
Initial documentation for implementing prototype | Project Manager | 2017-03-15 | 2017-03-28 | 13 |  | Not Started
Prototype 2
Meeting Agenda | Project Manager | 2017-04-04 | 2017-04-04 | 1 | 1 | Not Started | 1
Meeting | Project Team | 2017-04-05 | 2017-04-05 | 1 | 1 | Not Started | 1
Meeting Notes | Project Team | 2017-04-05 | 2017-04-05 | 1 | 1 | Not Started | 1
Report 4
Create Report | Project Team | 2017-04-13 | 2017-04-18 | 5 | 10 | Not Started
Feedback on Report | Project Team | 2017-04-20 | 2017-04-20 | 1 | 1 | Not Started
Submit Report 4 | Project Team | 2017-04-25 | 2017-04-25 | 1 | 0.25 | Not Started
Project
Updates to current Docs | Project Manager | 2017-04-20 | 2017-05-04 | 14 |  | Not Started
Two or more working prototypes | Development Team | 2017-04-20 | 2017-05-04 | 14 |  | Not Started
Final Report
Final Report Paper | Project Team | 2017-04-05 | 2017-05-16 | 41 |  | Not Started
Submit Report | Project Manager | 2017-05-16 | 2017-05-16 | 1 |  | Not Started
Presentation Coaching | Project Team | 2017-05-16 | 2017-05-16 | 1 |  | Not Started
Presentation | Project Team | 2017-05-18 | 2017-05-18 | 1 |  | Not Started
Launch |  | 2017-01-31 | 2017-05-18 | 107
Formulas:
Start = [Project Status:, row above]+[Days, row above]
Project Status: = Table1[[#This Row],[Start]]
Project Status: = [Project Status:, row above]

## Detailed Tasks
Project Name | Workflow JS Widget |  | Project Status: |  |  |  | <- | Values automatically update |  | Resources
Project Manager | Justin Goulet |  | Complete |  |  | 18 |  |  |  | Justin Goulet | Project Manager
Project Deliverable | 0 |  | In Progress |  |  | 3 |  |  |  | Chris Larsen | DBA / Developer
Scope Statement: | 0 |  | Not Started |  |  | 23 |  |  |  | Mikal Callahan | UX / UI Designer
|  |  | OverDue | [6 empty] | Brock Corbett | Developer
Start Date | 42766 |  | 0 | [6 empty] | Shaun-Inn Wu | Project Director
Expected End Date | 42873 |  | Note - Percentage is provided by ALL items completed divided by the amount of cells not empty | [6 empty] | Developers | Development Team
Overall Progress | 0.31579 | [8 empty] | All | Project Team
Tasks | Responsible | Start | End | Days | Hours | Status | isComplete | Person Assigned | Total Hours
Introduction to Course | Project Director | 2017-01-24 | 2017-01-24 | 1 | 0 | Complete | 1 | Shaun-Inn Wu
Syllabus / Project Introduction | Project Director | 2017-01-25 | 2017-01-31 | 6 | 0 | Complete | 1 | Shaun-Inn Wu
Client Presentation / Team Formation | Project Director | 2017-01-31 | 2017-01-31 | 1 | 0 | Complete | 1 | Shaun-Inn Wu
JAD 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Meeting Agenda | Project Manager | 2017-02-07 | 2017-02-07 | 1 | 0 | Complete | 1 | Justin Goulet
Meeting | Project Manager | 2017-02-08 | 2017-02-08 | 1 | 0 | Complete | 1 | Justin Goulet
Meeting Notes | Project Manager | 2017-02-09 | 2017-02-09 | 1 | 0 | Complete | 1 | Justin Goulet
Setup Client Communications | Project Manager | 2017-02-08 | 2017-02-08 | 1 | 0 | Complete | 1 | Justin Goulet
Research Possible Workflow Solutions | Project Manager | 2017-02-09 | 2017-02-22 | 13 | 0 | Complete | 1 | Justin Goulet
Create Sketch of Proposed Solution | Project Manager | 2017-02-22 | 2017-02-23 | 1 | 22 | Complete | 1 | Justin Goulet
Report 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Create Report | Project Team | 2017-02-10 | 2017-02-14 | 4 | 10 | Complete | 1 | All
Feedback on Report | Project Team | 2017-02-16 | 2017-02-16 | 1 | 1 | Complete | 1 | All
Submit Report 1 | Project Team | 2017-02-16 | 2017-02-16 | 1 | 0.25 | Complete | 1 | All
JAD 2 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
Meeting Agenda | Project Manager | 2017-02-21 | 2017-02-21 | 1 | 1 | Complete | 1 | Justin Goulet
Meeting | Project Team | 2017-02-22 | 2017-02-22 | 1 | 1 | Complete | 1 | All
Meeting Notes | Project Team | 2017-02-22 | 2017-02-22 | 1 | 1 | Complete | 1 | All
Report 2 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Create Report | Project Team | 2017-02-23 | 2017-02-27 | 4 | 10 | Complete | 1 | All
Feedback on Report | Project Team | 2017-02-28 | 2017-03-07 | 7 | 1 | In Progress | 0 | All
Submit Report 2 | Project Team | 2017-03-07 | 2017-03-07 | 1 | 0.25 | Not Started | 0 | All
Decision Matrix | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
D3 / D4 & Others: Cost / Features | Project Team | 2017-02-28 | 2017-03-01 | 1 | 0 | Complete | 1 | All
Create Editable Decision Matrix | Project Manager | 2017-02-28 | 2017-02-28 | 1 | 0 | Complete | 1 | Justin Goulet
Product | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
User Manual | Project Manager | 2017-02-28 | 2017-03-15 | 15 | 0 | In Progress | 0 | Justin Goulet
Skelaton Product | Development Team | 2017-02-28 | 2017-03-15 | 15 | 0 | In Progress | 0 | Developers
Prototype 1 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
Meeting Agenda | Project Manager | 2017-03-14 | 2017-03-14 | 1 | 1 | Not Started | 1 | Justin Goulet
Meeting | Project Team | 2017-03-15 | 2017-03-15 | 1 | 1 | Not Started | 1 | All
Meeting Notes | Project Team | 2017-03-15 | 2017-03-15 | 1 | 1 | Not Started | 1 | All
Report 3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Create Report | Project Team | 2017-03-23 | 2017-03-28 | 5 | 10 | Not Started | 0 | All
Feedback on Report | Project Team | 2017-03-30 | 2017-03-30 | 1 | 1 | Not Started | 0 | All
Submit Report 3 | Project Team | 2017-04-04 | 2017-04-04 | 1 | 0.25 | Not Started | 0 | All
Project | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Updates to current Docs | Project Manager | 2017-03-15 | 2017-03-28 | 13 | 0 | Not Started | 0 | Justin Goulet
Working prototype of simple theme | Development Team | 2017-03-15 | 2017-03-28 | 13 | 0 | Not Started | 0 | Developers
Complete code for implementing prototype | Development Team | 2017-03-15 | 2017-03-28 | 13 | 0 | Not Started | 0 | Developers
Initial documentation for implementing prototype | Project Manager | 2017-03-15 | 2017-03-28 | 13 | 0 | Not Started | 0 | Justin Goulet
Prototype 2 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
Meeting Agenda | Project Manager | 2017-04-04 | 2017-04-04 | 1 | 1 | Not Started | 1 | Justin Goulet
Meeting | Project Team | 2017-04-05 | 2017-04-05 | 1 | 1 | Not Started | 1 | All
Meeting Notes | Project Team | 2017-04-05 | 2017-04-05 | 1 | 1 | Not Started | 1 | All
Report 4 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Create Report | Project Team | 2017-04-13 | 2017-04-18 | 5 | 10 | Not Started | 0 | All
Feedback on Report | Project Team | 2017-04-20 | 2017-04-20 | 1 | 1 | Not Started | 0 | All
Submit Report 4 | Project Team | 2017-04-25 | 2017-04-25 | 1 | 0.25 | Not Started | 0 | All
Project | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Updates to current Docs | Project Manager | 2017-04-20 | 2017-05-04 | 14 | 0 | Not Started | 0 | Justin Goulet
Two or more working prototypes | Development Team | 2017-04-20 | 2017-05-04 | 14 | 0 | Not Started | 0 | Developers
Final Report | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
Final Report Paper | Project Team | 2017-04-05 | 2017-05-16 | 41 | 0 | Not Started | 0 | All
Submit Report | Project Manager | 2017-05-16 | 2017-05-16 | 1 | 0 | Not Started | 0 | Justin Goulet
Presentation Coaching | Project Team | 2017-05-16 | 2017-05-16 | 1 | 0 | Not Started | 0 | All
Presentation | Project Team | 2017-05-18 | 2017-05-18 | 1 | 0 | Not Started | 0 | All
Launch |  | 2017-01-31 | 2017-05-18

## Resources
Resource Sheet
Name | Role | Rate | Time Dimension | Time Worked | Accumulated Cost | Work Assigned | Work Completed
Justin Goulet | Project Manager |  |  |  |  | 0
Chris Larsen | DBA / Developer
Mikal Callahan | UX / UI Designer
Brock Corbett | Developer
Shaun-Inn Wu | Project Director
Developers | Development Team | 0 | N /A | N / A | 0
All | Project Team | 0